## Table 1
Edit the Header with Your Team ID StatusTracker 1/25/2024

## Table 2
PROJECT NUMBER | 31
PROJECT NAME | Automate R&D Workflow
PROJECT MENTOR (s | Suraj Bonagiri
Activity Name | Type | Responsible | Estimated Team Hours | Actual Hours | Status | Comments
See Instructions sheet for usage
Week 1 (January 16- January 21)
Fix meeting with client | Coordination | Atidipt | 0.5 | 0.3 | Done | What all to do be done in project
GIT Repository setup | Preparation | Shivam | 0.1 | 0.1 | Done | Team git repo
Client meeting | Coordination | Agrim | 1 | 1 | Done | Basic insights of the project
Team Meeting | Preparation | All | 1 | 1 | Done | Discussion on how to approach and do the project.
Week 2 (January 22 - January 28)
Client meeting | Coordination | Aniket | 0.5 | 1 | Done | What all to do be done in project
Status tracker | Documentation | Aditya | 0.5 | 0.5 | Done | Track each part of project
Project synopsis writeup | Documentation | All | 1 | 2 | Done | Detail description about the project
MoM | Documentation | Shivam,Aditya | 1 | 1 | Done | Short description of the meetings held
Team Meeting | Preparation | All | 1 | 2 | Done | Divide the project work
Taskade Account Creation | Preparation | All | 0.1 | 0.1 | Done | N/A
Week 3 (January 29 - February 4)
Client meeting | Coordination | All | 0.5 | - | Cancelled | Client cancelled
Status tracker | Documentation | Aditya | 0.5 | 0.5 | Done | Track each part of project
Learn MongoDB | Preparation | All | 6 | 10 | Done | N/A
Learn React | Preparation | All | 7 | 10 | Done | N/A
Start Working on Basic Website | Preparation | All | 8 | 10 | Done | Login page is ready
Week 4(February 5-February 11)
Team meeting | Preparation | All | 0.5 | 1 | Done | Discussion of what all to do next
Database for login page | Preparation | Aditya | 2 | 4 | Done | MongoDB database created
Status tracker | Documentation | Agrim | 0.5 | 0.5 | Done | Track each part of project
Week 5 (February 12-February 18)
Client meeting | Coordination | All | 0.5 | 1 | Done | Discussion of what all pages we need to create
Status tracker | Documentation | Shivam | 0.5 | 0.5 | Done | Track each part of project
Team meeting | Preparation | All | 0.5 | 1 | Done
Other Pages | Preparation | All | 6 |  | Done
Week 6 (February 19-February 25)
Client meeting | Coordination | All | 0.5 | 0.1 | Done | Give updates about the work, and next thing we need to do
Status tracker | Documentation | Atidipt | 0.5 | 0.1 | Done | Track each part of project
Team meeting | Preparation | All | 1 | 1.5 | Done | Discussion of what all work is done and what all needs to be done
Home Page | Preparation | Shivam | 1.5 | 2 | Done | Create a home page for the dashboard
Form Page | Preparation | Aditya,Atidipt | 2 | 1.5 | Done | Create a page where details of tools will be there
View Tools Page | Preparation | Agrim | 1 | 2.5 | Done | Create a page where all the tools ordered can be displayed
Status Update Page | Preparation | Aniket | 1.5 | 1 | Done | Track tools which are ordered
Week 7 (February 26-March 3 )
Client meeting | Coordination | All | 0.5 | 3 | Done | Give updates about the work, and next thing we need to do
Status tracker | Documentation | Agrim | 0.5 | 0.1 | Done | Track each part of project
Team meeting | Preparation | All | 1 | 1 | Done | Discussion of what all work is done and what all needs to be done
Css Part of the pages | Preparation | Agrim,Shivam | 2 | 2.5 | Done | Do CSS part of the pages made
Attach backend with the frontend | Preparation | Aditya,Aniket | 2 | 4 | Done | Connect the backend from local to mongodb atlas
Minor changes in the Page | Preparation | Atidipt | 1 | 2 | Done | Make some changes in purchase and status tracker page
Week 8 (March 4-March 10 )
Client meeting | Coordination | All | 0.5 | 0.1 | Done | Give updates about the work, and do live testing
Status tracker | Documentation | Atidipt | 0.5 | 0.2 | Done | Track each part of project
Team meeting | Preparation | All | 1 | 1 | Done | Discussion of what all work is done and what all needs to be done
Update status tracker page | Preparation | Agrim | 2 | 2 | Done | Make changes in the status tracker page
Add downloadable files in backend | Preparation | Aditya,Aniket | 2.5 | 3 | Done | Upload downloadable files in backend
Css and animation | Preparation | Shivam,Atidipt | 2 | 2.5 | Done | Add css and animation in the website
Live testing | Preparation | All | 1 | 1 | Done | Check each functionality with the client
Week 9 (March 11-March 17 )
Client meeting | Coordination | All | 0.5 |  | Cancelled | Cancelled by client
Status tracker | Documentation | Shivam | 0.5 | 0.2 | Done | Track each part of project
Team meeting | Preparation | All | 1 | 1 | Done | Discussion of what all work is done and what all needs to be done
Local host to local server | Preparation | Shivam | 1.5 |  | Done | The local host could be seen from any device
Add authentication routing | Preparation | Aniket,Atidipt | 2 | 1.5 | Done | Once the user is logged in then only redirect to other pages
Complete status tracker page | Preparation | Agrim | 2 | 3 | Done | Add various columns and actions in status tracker page
Adding downlodable files on webpage | Preparation | Aditya | 2.5 | 3 | Done | Add downloadable links in status tracker page
Week 10 (March 18-March 24 )
Client meeting | Coordination | All | 0.5 | 0.5 | Done | Cancelled by client
Status tracker | Documentation | Aniket | 0.5 | 0.5 | Done | Track each part of project
Team meeting | Preparation | All | 1 | 2 | Done | Discussion of what all work is done and what all needs to be done
R1 Presentation | Preparation | Shivam,Atidipt | 2 | 3 | Done | Creating a presentation for R1
Updating all the live documents | Preparation | Aditya,Aniket,Agrim | 2 | 2 | Done | Updating All the live documents
Final testing before R1 | Preparation | All | 1.5 | 1 | Done | Do a testing of the website before R1
Preparation for R2 | Preparation | All | 3 | 3 | Done | Plan what all needs to be done in R2
Week 11 (March 25-March 31 )
Client meeting | Coordination | All | 0.5 | 0.5 | Done | Discussed all the work done
Status tracker | Documentation | Aniket | 0.5 | 1 | Done | Track each part of project
Team meeting | Preparation | All | 1 | 1.5 | Done | Discussion of what all work is done and what all needs to be done
Client Office visit | Preparation | All | 4 | 5.5 | Done | Deployment in client office
Status Tracker Page update | Preparation | Agrim | 2 | 2.5 | Done | Add few options in status tracker page
Live testing | Preparation | All | 1 | 0.5 | Done | Check all the purchase functionality
Start working on R2 | Preparation | All | 2 |  | Done | Plan and divide each work for R2
Week 12 (April 01-April 07 )
Client meeting | Coordination | All | 0.5 | 0.5 | Done | Discussed all the work done
Status tracker | Documentation | Atidipt | 0.5 | 0.5 | Done | Track each part of project
Team meeting | Preparation | All | 1 | 1 | Done | Discussion of what all work is done and what all needs to be done
Client Office visit | Preparation | All | 4 | 4 | Done | To validate all corrections and updates
Updation of purchases pages | Preparation | Aniket | 4 | 5 | Done | Changes suggested by client to be implemented
Addition of Export to Excel option | Preparation | Shivam | 1.5 | 2 | Done | Check all the purchase functionality
Starting of Drone Testing page | Preparation | Atidipt | 2 | 3 | Done | Plan and divide each work for R2
Status Tracker Page update | Preparation | Agrim | 2 | 3 | Done | Add few options in status tracker page
Start working on R2 | Preparation | All | 5 | 6 | Done | Plan and divide each work for R2
Week 13 (April 08-April 14 )
Client meeting | Coordination | All | 0.5 | 0.1 | Done | Discussed all the work done
Status tracker | Documentation | Aditya | 0.5 | 0.5 | Done | Track each part of project
Team meeting | Preparation | All | 1 | 1 | Done | Discussion of what all work is done and what all needs to be done
Updation of purchases pages | Preparation | Aniket | 4 | 5 | Done | Changes suggested by client to be implemented
Project rescope change | Preparation | Shivam | 1 | 1 | Done | Project scope change so discuss what to do
Book a slot for drone testing | Preparation | Agrim | 3 | 4 | Done | Make a page for slot booking
Week 12 (April 15-April 21 )
Client meeting | Coordination | All | 0.5 | 0.1 | Done | Discussed all the work done
Status tracker | Documentation | Atidipt | 0.5 | 0.5 | Done | Track each part of project
Team meeting | Preparation | All | 1 | 1 | Done | Discussion of what all work is done and what all needs to be done
Search bar page | Preparation | Aditya | 2 | 4 | Done | Make a search page for tools
Leave approval page | Preparation | Aniket | 3 | 4 | Done | Make a page for leave approval of employees
Book a slot for drone testing | Preparation | Agrim | 3 | 4 | Done | Make a page for slot booking
Documentation | Preparation | Shivam | 2 | 3 | Done | Update all the live documents
Final testing of entire project | Preparation | All | 1 | 1 | Done | Have a final test of our project