## Table 1
Edit the Header with Your Team ID StatusTracker 1/25/2024

## Table 2
PROJECT NUMBER | 31
PROJECT NAME | Automate R&D Workflow
PROJECT MENTOR (s | Suraj Bonagiri
Activity Name | Type | Responsible | Estimated Team Hours | Actual Hours | Status | Comments
See Instructions sheet for usage
Week 1 (January 16- January 21)
Fix meeting with client | Coordination | Atidipt | 0.5 | 0.3 | Done | What all to do be done in project
GIT Repository setup | Preparation | Shivam | 0.1 | 0.1 | Done | Team git repo
Client meeting | Coordination | Agrim | 1 | 1 | Done | Basic insights of the project
Team Meeting | Preparation | All | 1 | 1 | Done | Discussion on how to approach and do the project.
Week 2 (January 22 - January 28)
Client meeting | Coordination | Aniket | 0.5 | 1 | Done | What all to do be done in project
Status tracker | Documentation | Aditya | 0.5 | 0.5 | Done | Track each part of project
Project synopsis writeup | Documentation | All | 1 | 2 | Done | Detail description about the project
MoM | Documentation | Shivam,Aditya | 1 | 1 | Done | Short description of the meetings held
Team Meeting | Preparation | All | 1 | 2 | Done | Divide the project work
Taskade Account Creation | Preparation | All | 0.1 | 0.1 | Done | N/A
Week 3 (January 29 - February 4)
Client meeting | Coordination | All | 0.5 | - | Cancelled | Client cancelled
Status tracker | Documentation | Aditya | 0.5 | 0.5 | Done | Track each part of project
Learn MongoDB | Preparation | All | 6 | - | Ongoing | N/A
Learn React | Preparation | All | 7 | - | Ongoing | N/A
Start Working on Basic Website | Preparation | All | 8 | - | Ongoing | Login page is ready
Week 4(February 5-February 11)
Team meeting | Preparation | All | 0.5 | 1 | Done | Discussion of what all to do next
Database for login page | Preparation | Aditya | 2 | 4 | Done | MongoDB database created
Status tracker | Documentation | Agrim | 0.5 | 0.5 | Done | Track each part of project
Week 5 (February 12-February 18)
Client meeting | Coordination | All | 0.5 | 1 | Done | Discussion of what all pages we need to create
Status tracker | Documentation | Shivam | 0.5 | 0.5 | Done | Track each part of project
Team meeting | Preparation | All | 0.5 | 1 | Done
Other Pages | Preparation | All | 6 |  | Ongoing
Week 6 (February 19-February 25)
Client meeting | Coordination | All | 0.5 |  | Planned | Give updates about the work, and next thing we need to do
Status tracker | Documentation | Atidipt | 0.5 |  | Planned | Track each part of project
Team meeting | Preparation | All | 1 |  | Planned | Discussion of what all work is done and what all needs to be done
Home Page | Preparation | Shivam | 1.5 |  | Planned | Create a home page for the dashboard
Form Page | Preparation | Aditya,Atidipt | 2 |  | Planned | Create a page where details of tools will be there
View Tools Page | Preparation | Agrim | 1 |  | Planned | Create a page where all the tools ordered can be displayed
Status Update Page | Preparation | Aniket | 1.5 |  | Planned | Track tools which are ordered
Week 7 (February 26-March 3 )